Fuel Reconciliation Manager

MVP v1 Scope Freeze

Windows desktop fuel usage and billing reconciliation app

Target acceptance period: May 2026
Version: 1.0
Status: Draft for client review

| Field | Value |
| --- | --- |
| Document title | Fuel Reconciliation Manager — MVP v1 Scope Freeze |
| Project | Windows desktop fuel usage and billing reconciliation application |
| Prepared for | Client proposal / project specification |
| Target acceptance period | May 2026 |
| Version | 1.0 |
| Status | Draft for review |
| Purpose | Freeze MVP v1 scope, not-to-build list and change request triggers before development starts. |

# 1. Purpose

This document freezes the MVP v1 scope for the Fuel Reconciliation Manager. It defines what is included in the first build, what is explicitly excluded, and which changes require a formal change request. The purpose is to prevent uncontrolled scope expansion during development, testing and acceptance.

Scope freeze principle: MVP v1 is designed to prove the full end-to-end reconciliation workflow on the agreed May 2026 sample data, not to support every possible supplier layout, customer template, deployment model or reporting variation.

# 2. Scope Freeze Principles

| ID | Principle | Meaning for MVP v1 |
| --- | --- | --- |
| SF-01 | End-to-end first | MVP v1 must deliver one complete usable workflow: import, validate, reconcile, review, branch report, PDF export and audit. |
| SF-02 | Sample-driven parsing | PDF and Excel parsing is limited to agreed sample layouts unless a change request extends parser scope. |
| SF-03 | Deterministic reconciliation | Matching rules, tolerances, snapshots and audit records must produce repeatable results. |
| SF-04 | Local desktop delivery | MVP v1 is a local Windows desktop app, not a shared cloud/server product. |
| SF-05 | Configuration is controlled | Aliases, templates, tolerances and report defaults are included only to the extent needed for MVP acceptance. |
| SF-06 | No silent expansion | New supplier formats, extra exports, new report types or integration work require change request approval. |

# 3. MVP v1 In Scope

| ID | Scope Area | Included in MVP v1 |
| --- | --- | --- |
| IN-01 | Windows application | Self-contained Windows desktop build delivered as portable folder or lightweight installer. |
| IN-02 | Required input files | Three mandatory input slots: Supplier Statement, Branch Litres Workbook and Cars+ Export. |
| IN-03 | Supplier PDF import | Parsing of agreed supplier PDF layouts used for development and acceptance testing, including agreed Mobil and Farmlands/Caltex samples. |
| IN-04 | Excel import | Mandatory support for .xlsx branch litres workbook and .xlsx Cars+ export. Optional .xls/.xlsb/.csv only if included in agreed samples. |
| IN-05 | Validation and mapping | File-level and row-level validation, required-field checks, preview rows, basic manual column mapping and saved mapping templates. |
| IN-06 | Normalisation | Normalisation of branch, RA, rego, dates, litres and amounts according to fixed MVP rules/settings. |
| IN-07 | Reconciliation engine | Supplier-to-branch and branch-to-Cars+ matching using RA primary matching and rego/date/litres fallback. |
| IN-08 | Exception statuses | Matched, Unbilled, Variance, DuplicatePossible, MissingRA, RegoMismatch, SupplierOnly, CarsOnly and ReviewRequired item statuses. |
| IN-09 | Review workflow | Review Queue, exception detail, manual resolution with notes and manual linking where required. |
| IN-10 | Branch Report | Branch selector, run context, totals, exception tables, notes, prepared/approved fields and export history. |
| IN-11 | PDF export | Branch-level PDF export using agreed report template/stationery, export settings, metadata and export history. |
| IN-12 | History/Audit | Import history, validation results, reconciliation runs, manual actions, lifecycle changes and PDF export records. |
| IN-13 | Period lifecycle | Draft, Files Imported, Validated, Reconciled, Review Required, Reviewed, Approved, Closed, plus controlled Reopened state/flag. |
| IN-14 | Dashboard | Period overview, input readiness, KPI summary, alerts, branch summary and next-action CTAs. |
| IN-15 | Settings and rules | MVP settings required to complete acceptance on the agreed sample files: branch aliases, supplier/site aliases, column mappings, matching tolerances, average fuel price/estimated recovery assumptions, and report/export defaults. Advanced admin platform features are not included in MVP v1 unless explicitly added by change request. |
| IN-16 | Error/empty/loading states | Key operational states for first launch, partial imports, validation failures, running reconciliation, PDF export and closed periods. |
| IN-17 | Performance and reliability | Measured MVP targets for import, validation, reconciliation, PDF export, UI responsiveness and crash-safe committed data. |
| IN-18 | Security and data handling | Local-only operation, documented storage paths, restricted local folders where feasible, audit identity via Windows username for MVP. |
| IN-19 | Accessibility and UX | Keyboard-accessible primary flows, visible focus, high contrast support, readable tables and clear CTAs. |
| IN-20 | Documentation | User guide, setup/admin notes, known limitations, third-party dependency list and acceptance test package required for MVP handover and acceptance. These are release deliverables for MVP v1, not additional product features. |

# 4. Explicitly Out of Scope for MVP v1

| ID | Out-of-Scope Item | Not Included in MVP v1 |
| --- | --- | --- |
| OUT-01 | Arbitrary supplier PDF layouts | The app is not expected to parse any supplier PDF that was not included in agreed sample layouts. |
| OUT-02 | Scanned PDF OCR | OCR for scanned statements is excluded unless separately approved. Digital/text PDF parsing only. |
| OUT-03 | Unlimited Excel templates | Support for unknown branch/Cars+ templates beyond agreed layouts is excluded. New templates require change request. |
| OUT-04 | Cloud storage/sync | No cloud database, cloud storage, shared tenant, cloud sync or web portal. |
| OUT-05 | Multi-user server deployment | MVP is local desktop with one active local user/session per local database. Shared DB/server concurrency is excluded. |
| OUT-06 | Full identity management | No full login system, SSO, Azure AD/Entra integration or complex role management. Windows username audit is sufficient for MVP. |
| OUT-07 | Accounting/Cars+ write-back | No automatic posting, write-back, API update or billing creation in Cars+ or accounting systems. |
| OUT-08 | Bank/accounting integrations | No integration with Xero, MYOB, SAP, Oracle, bank feeds or ERP systems. |
| OUT-09 | Advanced analytics suite | No separate BI dashboards, forecasting, anomaly ML, trend analysis or multi-year management reporting beyond MVP dashboard. |
| OUT-10 | Advanced masking/privacy UI | Basic data minimisation is in scope; configurable masking policy UI is out unless separately approved. |
| OUT-11 | Archive/backup management UI | Basic documentation of local database/log locations is in scope; full backup/restore/archive UI is excluded. |
| OUT-12 | Automatic updates | Auto-update, update signing infrastructure and remote update checks are excluded. Delivery uses controlled installer/package. |
| OUT-13 | Notification system | Email notifications, Teams/Slack alerts, scheduled reminders and automated escalations are excluded. |
| OUT-14 | Mobile/tablet/web client | No mobile app, browser-based app or tablet-specific UI. |
| OUT-15 | Custom report builder | Only agreed Branch Report/PDF template is in scope; arbitrary custom report designer is excluded. |
| OUT-16 | Multiple stationery templates | Only agreed default stationery/template is in scope unless additional templates are approved. |
| OUT-17 | Bulk historical migration | Importing and reconciling historical months beyond the agreed acceptance sample is excluded unless separately scoped. |
| OUT-18 | Automated legal/compliance certification | Accessibility/security best practices are included, but formal certification or penetration testing is excluded unless contracted. |

# 5. Change Request Triggers

The following changes are not accepted as informal tweaks. They require review of cost, schedule, testing impact and acceptance criteria before implementation.

| ID | Trigger | Requires Change Request When... |
| --- | --- | --- |
| CR-01 | New supplier PDF layout | A supplier statement layout is not covered by the agreed parser samples. |
| CR-02 | Scanned/OCR PDF support | The client provides scanned/image-based statements that require OCR or visual extraction. |
| CR-03 | New Excel template | Branch litres or Cars+ export structure differs materially from agreed templates. |
| CR-04 | Additional input file type | Any new required input source is requested, such as fuel card master, customer invoice export or branch mapping file. |
| CR-05 | New reconciliation rule | Business requests new matching rules, exceptions, tolerances or status categories beyond MVP rules. |
| CR-06 | Changed correctness reference | Manual reconciliation reference result changes after development baseline is agreed. |
| CR-07 | New report or PDF section | New report types, extra report sections, new stationery or additional PDF variants are requested. |
| CR-08 | Write-back integration | Any request to update Cars+, accounting system, ERP or external system from the app. |
| CR-09 | Multi-user/server mode | Shared database, concurrent multi-user access, permissions server or web portal is requested. |
| CR-10 | Advanced security/compliance | Database encryption, SSO, advanced masking, audit retention workflow or formal certification is requested. |
| CR-11 | Backup/archive UI | Archive, purge, restore or scheduled backup feature is requested. |
| CR-12 | Notification/escalation workflow | Email/Teams reminders, overdue workflows or assignment notifications are requested. |
| CR-13 | Major UI redesign | Significant UX redesign, dark mode/high contrast design system expansion or custom branding beyond MVP screens. |
| CR-14 | Performance target increase | Data volume or performance target exceeds agreed MVP test data/profile. |
| CR-15 | Additional acceptance period | New months or historical batches are added to acceptance scope beyond agreed May 2026 sample. |

# 6. Scope Assumptions and Dependencies

| ID | Assumption / Dependency | Impact if Not Met |
| --- | --- | --- |
| AS-01 | Client provides agreed May 2026 sample files for all three input slots. | Parsing, reconciliation and acceptance testing cannot be completed accurately. |
| AS-02 | Client provides manual reconciliation reference result for May 2026. | Correctness cannot be verified against the client process. |
| AS-03 | Supplier PDF samples are digital/text PDFs, not scanned images. | OCR would require a change request. |
| AS-04 | Branch and Cars+ Excel files use agreed templates or templates that can be mapped during MVP. | Unknown templates may require change request. |
| AS-05 | Client confirms matching tolerance defaults before acceptance. | Tolerance changes after baseline may require re-test or change request. |
| AS-06 | Client provides logo/stationery requirements for PDF report. | PDF template may be delivered as close approximation until final stationery is supplied. |
| AS-07 | MVP deployment target is a modern Windows PC. | Unsupported OS/runtime constraints may require packaging changes. |
| AS-08 | MVP uses local SQLite database and local file storage. | Shared/team deployment changes require additional architecture. |

# 7. Scope Freeze Acceptance Gate

MVP v1 scope is considered frozen when the following conditions are met:

| Gate ID | Acceptance Gate | Required Evidence |
| --- | --- | --- |
| GATE-01 | Input samples agreed | Supplier PDF, branch workbook and Cars+ export samples stored in project test package. |
| GATE-02 | Reference result agreed | Manual reconciliation reference result documented for May 2026. |
| GATE-03 | In/out scope accepted | Client confirms MVP v1 in-scope and out-of-scope lists. |
| GATE-04 | Change request process accepted | Client agrees that new layouts, templates, reports, integrations or deployment changes require CR. |
| GATE-05 | PDF template baseline accepted | Client provides or approves report stationery/template baseline. |
| GATE-06 | MVP defaults accepted | Default tolerances, financial assumptions and role assumptions accepted or marked for confirmation. |
| GATE-07 | Delivery package accepted | Expected build, source, docs, tests and known limitations deliverables agreed. |

# 8. Change Request Process

| Step | Action | Output |
| --- | --- | --- |
| 1 | Raise change request | Change request title, requester, date, description and reason. |
| 2 | Classify impact | Affected area: parser, UI, reconciliation, reports, security, packaging, docs or tests. |
| 3 | Estimate impact | Estimate cost, schedule, testing effort and risk. |
| 4 | Approve or defer | Client approves for MVP, moves to v1.1/v2 backlog, or rejects. |
| 5 | Update scope docs | Accepted changes update requirements, acceptance criteria, test package and known limitations. |

| Field | Description |
| --- | --- |
| Change Request ID | Unique reference, e.g. CR-2026-001. |
| Requested by | Client/user requesting the change. |
| Date requested | Date submitted. |
| Description | What is requested. |
| Reason / business value | Why the change is needed. |
| Affected scope area | Parser, reconciliation, report, PDF, UI, security, performance, packaging, documentation, etc. |
| Acceptance criteria | How the change will be verified. |
| Impact estimate | Cost/schedule/testing/risk impact. |
| Decision | Approved for MVP, deferred, rejected, or needs clarification. |

# 9. Candidate Backlog for Later Versions

| Priority | Candidate Item | Notes |
| --- | --- | --- |
| v1.1 | Additional supplier PDF layouts | Add only after MVP parser is stable and new samples are provided. |
| v1.1 | Additional branch/Cars+ mapping templates | Useful if client has multiple branch workbook layouts. |
| v1.1 | Backup/archive utility | Add if retention/database size becomes operational concern. |
| v1.1 | Improved permission management | Move from fixed groups to configurable users/roles. |
| v2 | OCR fallback for scanned PDFs | Requires separate evaluation and accuracy testing. |
| v2 | Shared database / multi-user mode | Requires concurrency, locking, authentication and deployment architecture. |
| v2 | External system integration | Cars+/accounting write-back or API integration. |
| v2 | Advanced reporting and analytics | Trend dashboards, branch comparisons, management packs. |

# 10. Scope Freeze Sign-off

| Role | Name | Date | Signature / Approval |
| --- | --- | --- | --- |
| Client sponsor |  |  |  |
| Client operations/reconciliation owner |  |  |  |
| Developer / delivery owner |  |  |  |

By approving this document, the parties agree that MVP v1 scope is frozen according to the in-scope, out-of-scope and change request rules defined above.